## Sprint 1
|  |  | 2021-03-28 | 2021-03-29 | 2021-03-30 | 2021-03-31 | 2021-04-01 | 2021-04-02 | 2021-04-03 | 2021-04-04 | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-09 | 2021-04-10
Task | Names | Story Points | Day 1 | Day 2 | Day 3 | Day. 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
1. Initial boilerplate code | Himaja | 1 | bar: 2021-03-31
2. Various pages and directory structure | Himaja | 3 | 2021-04-02: 3
3. Sidebar and Navbar items creation | Himaja | 1 | bar: 2021-04-03
4. MongoDB connection and table Schemas | Himaja | 5 | 2021-04-08: 5
5. Authentication Authorization middleware | Himaja | 1 | bar: 2021-04-08
6. User logout and redirects | Himaja | 1 | bar: 2021-04-06
7. Admin Create Account page - Frontend | Chandra Lekha | 5 | 2021-04-05: 5
8. Create Accout page input validations | Chandra Lekha | 3 | 2021-04-09: 3
|  | 20 | 20 | 20 | 20 | 19 | 19 | 16 | 15 | 15 | 10 | 9 | 9 | 3 | 0 | 0

## Sprint 2
|  |  | 2021-04-11 | 2021-04-12 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-18 | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-24
Task | Names | Story Points | Day 1 | Day 2 | Day 3 | Day. 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
1. Handle submission create account page (ADMIN) | Chandra Lekha | 3 | 2021-04-12: 3
2. Backend for Create accout page (ADMIN) | Chandra Lekha | 5 | 2021-04-14: 5
3. Frontend for Delete Account page (ADMIN) | Himaja | 5 | 2021-04-13: 5
4. Backend for Delete Account page (ADMIN) | Himaja | 5 | 2021-04-15: 5
5. Frontend for New Transfer page (USER) | Chandra Lekha | 7 | 2021-04-16: 7
6. Authentication, Authorization (USER, ADMIN) | Himaja | 1 | bar: 2021-04-16
7. Frontend New Transfer page input field validation (USER) | Chandra Lekha | 1 | bar: 2021-04-18
8. Backend New Transfer page (USER) | Chandra Lekha | 7 | 2021-04-20: 7
9. Connecting to mongoDB on mongoDB Atlas | Sagnik | 5 | 2021-04-16: 5
10. Frontend layout Transactions page (USER) | Anjali | 5 | 2021-04-17: 5
11. New Transfer page response handling (USER) | Chandra Lekha | 1 | bar: 2021-04-22
|  | 45 | 45 | 42 | 37 | 32 | 27 | 14 | 9 | 8 | 8 | 1 | 1 | 0 | 0 | 0

## Sprint 3
|  |  | 2021-04-25 | 2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30 | 2021-05-01 | 2021-05-02 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-05-08
Task | Names | Story Points | Day 1 | Day 2 | Day 3 | Day. 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
1. Hosting on AWS | Sagnik | 5 | 2021-04-26: 5
2. Frontend Accounts page (USER) | Sagnik | 3 | 2021-04-29: 3
3. Frontend Manual Transfer (ADMIN) | Chandra Lekha | 5 | 2021-04-30: 5
4. Backend Manual Transfer (ADMIN) | Chandra Lekha | 5 | 2021-05-03: 5
5. Frontend styling and icon | Himaja | 1 | bar: 2021-05-01
6. Backend Transactions page (USER) | Himaja | 5 | 2021-05-02: 5
7. Frontend Transactions page (USER) | Himaja | 5 | 2021-05-04: 5
8. Remove unused components | Anjali | 1 | bar: 2021-05-07
9. Backend Transactions page bug fix (USER) | Himaja | 3 | 2021-05-08: 3
10. External Transfer Bug fix (USER, ADMIN) | Chandra Lekha | 1 | bar: 2021-05-08
|  | 34 | 34 | 29 | 29 | 29 | 26 | 21 | 20 | 15 | 10 | 5 | 5 | 5 | 4 | 0

## Sprint 4
|  |  | 2021-05-09 | 2021-05-10 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14
Task | Names | Story Points | Day 1 | Day 2 | Day 3 | Day. 4 | Day 5 | Day 6
1. Styling fix | Anjali | 1 | bar: 2021-05-09
2. Frontend Accounts page styling (USER) | Sagnik | 3 | 2021-05-09: 3
3. Account Number table schema | Anjali | 5 | 2021-05-10: 5
4. Frontend create link from Accounts to Transactions page (USER) | Sagnik | 1 | bar: 2021-05-10
5. Frontend handle link from accounts page to transactions page (USER) | Himaja | 1 | bar: 2021-05-11
6. Backend W/R from DB instead of file | Chandra Lekha | 1 | bar: 2021-05-11
7. Frontend bug fix and styling | Chandra Lekha | 1 | bar: 2021-05-12
|  | 13 | 9 | 3 | 1 | 0 | 0 | 0